## Sheet1
2016-10-27
Task List
# | Task | status
1 | unit converter & validation for textboxes & comboboxes | done
2 | configuration file | done
3 | communication sequence with BBB | in progress
4 | save project | done
5 | open project | done
6 | Error control
7 | Implement TML LIB commands | done
8 | Attach soulutions protocol to system | in progress
9 | Emengency stop button | done
10 | BBB control flow algorithm | in progress
11 | PID for position & speed command algorithm
12 | GPS tracking algorithm
13 | orientation in general settings from 0-360 to nX360 | done
14 | offset/homing add units | done
15 | motion state: split for pan and tilt | done
16 | save preset to XML file | done
17 | communuication protocol with controller over Ethernet | done
18 | communuication protocol with controller over RS-232 | in progress
19 | Gui design
20 | Debug after finishing TML state
21 | Debug after finishing IMU state
22 | Debug after finishing GPS state
23 | GUI stabilization layer | in progress
24 | GUI GPS layer
25 | Application start: stay in current implementation or change? - stay | done
26 | PT setup files, attach to application without letting the user to chose manually, every part number will hold the same setup file | in progress
27 | Define part numbers for the different systems implementations
28 | Software LSP&LSP in general settings
29 | Protections for position speed and current
30 | Main panel TS | done
31 | Communcation with TS Eth' | done
32 | Communication with TS RS-232 | done
33 | Communication settings | done
34 | General settings | done
35 | Preset - implementatio changes | done
36 | Preset GPS | done
37 | Documentation
38 | Help
39 | Registers status from TS | done
40 | Registers status fromBBB | done
41 | PID for position & speed command window | done
42 | Read Current Encoder and Ration for general settings
43 | Link main panel with the configuration file | done
44 | Set min/max position in the main panel according to the user orientation | done
45 | preset selection - after add presets add them to the combobox | done
46 | Attach offset to position commands
47